## Dashboard
Active Projects |  | 11 | Scope & Estimate |  | 9 | Completed Projects |  | 51 | Applications |  | 27 | Initial Walks |  | 22 | PLS DO NOT TOUCH ANYTHING IN THIS BOX
| Ida | 7 |  | Ida | 5 |  | Ida | 37 |  | Ida | 10 |  | Ida | 17 | starts | active | completes | totals
| OCD | 0 |  | OCD | 0 |  | OCD | 0 |  | OCD | 0 |  | OCD | 0 | jan | 0 | 2 | 2
| VHRMP | 1 |  | VHRMP | 3 |  | VHRMP | 3 |  | VHRMP | 2 |  | VHRMP | 5 | feb | 0 | 8 | 8
| Viatris | 0 |  | Viatris | 0 |  | Viatris | 2 |  | Viatris | 0 |  | Viatris | 0 | march | 1 | 7 | 8
| OAHMP | 3 |  | OAHMP | 1 |  | OAHMP | 8 |  | OAHMP | 15 |  | OAHMP | 0 | april | 0 | 4 | 4
| Tornado | 0 |  | Tornado | 0 |  | Tornado | 1 |  | Tornado | 0 |  | Tornado | 0 | may | 0 | 5 | 5
| OH | 0 |  | OH | 0 |  | OH | 0 |  | OH | 0 |  | OH | 0 | june | 0 | 1 | 1
| RAF | 0 |  | RAF | 0 |  | RAF |  |  | RAF |  |  | RAF |  | july | 0 | 5 | 5
[15 empty] | aug | 0 | 0 | 0
[15 empty] | sept | 0 | 0 | 0
Starts By Month |  | Year Goal | 94 | Year Actuals | 32 |  | Remaining | 62 | [6 empty] | oct | 0 | 0 | 0
| January | Goal | 7 | April | Goal | 7 | July | Goal | 9 | October | Goal | 10 |  |  | nov | 0 | 0 | 0
|  | Actual | 2 |  | Actual | 4 |  | Actual | 5 |  | Actual | 0 |  |  | dec | 0 | 0 | 0
| February | Goal | 6 | May | Goal | 7 | August | Goal | 9 | November | Goal | 9 |  |  | closeouts
|  | Actual | 8 |  | Actual | 5 |  | Actual | 0 |  | Actual | 0 |  |  | jan | 0 | 8 | 8
| March | Goal | 6 | June | Goal | 7 | September | Goal | 11 | December | Goal | 6 |  |  | feb | 0 | 9 | 9
|  | Actual | 7 |  | Actual | 1 |  | Actual | 0 |  | Actual | 0 |  |  | march | 1 | 6 | 6
[15 empty] | april | 0 | 6 | 6
Completes By Month |  |  |  | Goal | 94 |  | YTD Actuals | 49 |  | Remaining | 45 |  |  |  | may | 0 | 8 | 8
| January | Goal | 6 | April | Goal | 6 | July | Goal | 7 | October | Goal | 11 |  |  | june | 0 | 4 | 4
|  | Actual | 8 |  | Actual | 6 |  | Actual | 6 |  | Actual | 0 |  |  | july | 0 | 6 | 6
| February | Goal | 7 | May | Goal | 7 | August | Goal | 9 | November | Goal | 10 |  |  | aug | 0 | 2 | 2
|  | Actual | 9 |  | Actual | 8 |  | Actual | 2 |  | Actual | 0 |  |  | sept | 0 | 0 | 0
| March | Goal | 6 | June | Goal | 7 | September | Goal | 9 | December | Goal | 9 |  |  | oct | 0 | 0 | 0
|  | Actual | 6 |  | Actual | 4 |  | Actual | 0 |  | Actual | 0 |  |  | nov | 0 | 0 | 0
[15 empty] | dec | 0 | 0 | 0
| Project Managers Numbers |  |  |  | Client Services | Active | SOW | Initial Walk | Apps in Progress | Totals
| PM1 | Active | 2 |  |  | 0 | 0 | 0 | 0 | 0
|  | S&E | 0 |  | CSC1 | 2 | 0 | 0 | 3 | 5
|  | Walks | 2 |  |  | 0 | 0 | 0 | 0 | 0
|  | Completes | 21 |  | CSC2 | 14 | 9 | 22 | 22 | 67
|  | Total | 25
| PM2 | Active | 2
|  | S&E | 5
|  | Walks | 16
|  | Completes | 20
|  | Total | 43
| PM3 | Active | 3
|  | S&E | 4
|  | Walks | 1
|  | Completes | 8
|  | Total | 16
| PM4 | Active | 1
|  | S&E | 0
|  | Walks | 0
|  | Completes | 2
|  | Total | 3

## Forecasting
FORECAST |  | January | February | March | April | May | June | July | August | September | October | November | December
| Completes | 6 | 7 | 6 | 6 | 7 | 7 | 7 | 5 | 7 | 6 | 7 | 5
| Notice to Proceed's issued | 7 | 6 | 6 | 7 | 7 | 7 | 9 | 7 | 6 | 8 | 5 | 5 | 80
Internal | OCD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
| OAHMP | 0 | 1 | 0 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 15
| VHRMP | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 2 | 2 | 2 | 2 | 1 | 13
| Ida | 2 | 7 | 6 | 5 | 2 | 5 | 3 | 2 | 2 | 2 | 2 | 1 | 39
| Solution 2 |  |  |  | 0 | 3 | 0 | 3 | 3 | 2 | 3 | 1 | 1 | 16 | 16
| NTP's (Goal) | 2 | 9 | 6 | 7 | 8 | 6 | 8 | 9 | 8 | 9 | 7 | 3 | 82
| NTP's (Projected) | 2 | 8 | 7 | 8 | 8 | 6 | 6 | 7 | 6 | 6 | 6 | 2 | 72
NTP Tier 1 ($10k cap) |  | 1 | 3 | 2 | 3 | 3 | 2 | 3 | 4 | 4 | 3 | 2 |  | 30 | 85
Client Name |  | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX
Address |  | Pailet Ave | Tennessee St | Bellemeade Blvd | Lesan Dr | Azalea Dr. | Palmyra St | Wakefield Dr | Ursulines Ave | Meadows Blvd
PM + CSC |  | HR/SZ | PN/CS | PN/CS | HR/SZ | PN/KA | PN/ET | PN/KA | AD/KA | PN/KA
Funding Type |  | Ida | Ida | Ida | Ida | Ida | Ida | Ida | VHRMP | VHRMP | OAHMP | OAHMP
Volunteer #s |  | 0 | 0 | 3 | 4 | 0 | 2 | 0 | 0 | 0
Project Cost |  | 5045.45 | $ | 16500 | 4700.1 | 6000 | 1600 | 5600 | 11000 | $ | $ | $
Client Name |  |  | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX
Address |  |  | Lily St | Tennessee St | Dauphine St | Lavender | Livingston Ave | Mayo Ave | Bacchus Dr
PM + CSC |  |  | HR/CS | PN/CS | AD/SZ | AD/KA | AD/ET | AD/KA | AD/KA
Funding Type |  |  | Ida | Ida | OAHMP | OAHMP | Ida | OAHMP | OAHMP | OAHMP | OAHMP | OAHMP
Volunteer #s |  |  | 15-18 | 0 | 0 | 0 |  | 0 | 0
Project Cost |  |  | 6000 | 4000 | 2840 | 4000 | 13658.52 | 4000 | $ | $ | $ | $
Client Name |  |  | XXX |  | XXX | XXX |  | XXX | XXX | XXX | XXX
Address |  | PN/CS: Fern St; HR/SZ: Ja-Don Dr; PN/KA: St. Philip Street; PN/KA: Vincent St; AD/KA: Royal St | Nicolle Blvd
PM + CSC |  | PN/CS: AD/SZ; HR/SZ: HR/SZ; PN/KA: HR/SZ; PN/KA: AD/KA; AD/KA: AD/KA | PN/KA
Funding Type |  |  | OAHMP |  | OAHMP - Bayou | OAHMP |  | OAHMP | OAHMP | OAHMP | VHRMP
Volunteer #s |  | PN/CS: 0; HR/SZ: 0; PN/KA: 0; PN/KA: 0; AD/KA: 0
Project Cost |  |  | 4000 |  | 3800 | 2800 |  | 4000 | $ | $ | $
Client Name |  | PN/CS: XXX; AD/KA: XXX; PN/KA: XXX
Address |  | PN/CS: Miles Dr; AD/KA: Daisy Ln; PN/KA: Prosperity St
PM + CSC |  | PN/CS: PN/CS; AD/KA: PN/KA; PN/KA: AD/KA
Funding Type |  | PN/CS: Ida; AD/KA: VHRMP; PN/KA: Ida?
Volunteer #s |  | PN/CS: 3; AD/KA: 0; PN/KA: 0
Project Cost |  | PN/CS: 4860.67; AD/KA: 5000; PN/KA: 7000
NTP Tier 2 ($20k cap) |  |  | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 2 | 3 | 2 | 23
Client Name |  |  | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX
Address |  |  | Tulane St | Palm St | Lauradale Dr | Park Blvd | Frenchmen St | Dolly St | Bishop Dr. | Helis Dr. | Pailet Ave | North Sibley St. | Josephine St
PM + CSC |  |  | HR/CS | HR/CS | PN/KA | HR/KA | PN/KA | PN/KA | PN/KA | PN/KA | AD/KA | PN/KA | PN/KA
Funding Type |  |  | Ida - Bayou | Ida | Ida | Ida | Ida | Ida | Ida/Roof | Ida | Ida | Ida/Roof | VHRMP
Volunteer #s |  |  | 5 | 5 | 8 | 6 | 0 | 0 | 0 | 2023-10-15 | 5 | 0
Project Cost |  |  | 19000 | 15000 | 6000 | 12000 | 17500 | $ | 21000 | $ | 15000 | $ | $
Client Name |  |  | XXX | XXX | XXX | XXX | XXX | XXX |  |  | XXX | XXX | XXX
Address |  |  | Dakin St | Marywood Ct | Hwy 15 | Bayou Black Dr | Ashley Dr. | Bishop Dr. |  |  | Dumaine St | Angela St. | Lafaye
PM + CSC |  |  | PN/CS | HR/SZ | HR/SZ | HR/SR | PN/KA | PN/KA |  |  | PN/KA | PN/KA | PN/KA
Funding Type |  |  | Ida | Ida | Ida- Bayou | Sol 2/Bayou | Ida | Ida/Roof |  |  | Ida/Roof | VHRMP | Ida/Roof
Volunteer #s |  |  | 0 | 8 | 4 | 0 | 0 | 0 |  |  | 15
Project Cost |  |  | 8000 | 20000 | 23000 | 13000 | 12000 | $ |  |  | $ | $ | $
Client Name |  |  | HR/CS: XXX; HR/CS: XXX; PN/KA: XXX; PN/KA: XXX
Address |  |  | HR/CS: Constantine Dr; HR/CS: N Roman St; PN/KA: Pailet Ave; PN/KA: Angelique
PM + CSC |  |  | HR/CS: HR/SZ; HR/CS: PN/SZ; PN/KA: PN/KA; PN/KA: PN/KA
Funding Type |  |  | HR/CS: Ida; HR/CS: Ida; PN/KA: Ida; PN/KA: Ida/Roof
Volunteer #s |  |  | HR/CS: 5; HR/CS: 15; PN/KA: 0
Project Cost |  |  | HR/CS: 23000; HR/CS: 15500; PN/KA: 12600; PN/KA: $
Client Name
Address
PM + CSC
Funding Type
Volunteer #s
Project Cost
NTP Tier 3 + |  | 1 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 1 |  | 19
Client Name |  | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX
Address |  | Caluda Ln | Bengal Rd | Clay St | Bourg Dr | Aberdeen | Pasteur Blvd | Nicolle Blvd | Stephanie St | Renaud St | Mansfield St | Ole Miss Dr
PM + CSC |  | HR/CS | PN/CS | AD/SZ | HR/SZ | HR/KA | KA/HR | HR/SZ | PN/KA | PN/KA | PN/KA | PN/KA
Funding Type |  | Ida | Ida | VHRMP | Ida-Bayou | VHRMP | VHRMP | Soultion 2 | Ida/ Bayou | VHRMP/Bayou/Roof | VHRMP | VHRMP
Volunteer #s |  | 25 | 10 | 0 | 15 | 0 | 20 | 0 | 0 | 0 | 10
Project Cost |  | 35000 | 25000 | 39000 | 42000 | 29000 | $65k | 74100 | 36000 | $ | $ | $
Client Name |  | PN/CS: XXX; AD/SZ: XXX; HR/SZ: XXX; HR/KA: XXX; KA/HR: XXX; PN/KA: XXX
Address |  | PN/CS: Solon St; AD/SZ: Chimney Ln; HR/SZ: N Derbigny St; HR/KA: Tupelo St; KA/HR: Chippewa St; PN/KA: Acorn Dr
PM + CSC |  | PN/CS: HR/CS; AD/SZ: PN/SZ; HR/SZ: SZ/HR; HR/KA: HR/SR; KA/HR: PN/KA; PN/KA: PN/KA
Funding Type |  | PN/CS: Ida; AD/SZ: Ida; HR/SZ: VHRMP; HR/KA: Solution 2; KA/HR: Viatris/Ida; PN/KA: Ida/Roof
Volunteer #s |  | PN/CS: 0; AD/SZ: 6; HR/SZ: 0; HR/KA: 0; KA/HR: 12; PN/KA: 15
Project Cost |  | PN/CS: 32000; AD/SZ: 25000; HR/SZ: 20000; HR/KA: 20000; KA/HR: 40000; PN/KA: $
Client Name |  | HR/SZ: XXX; HR/KA: XXX; KA/HR: XXX; HR/SZ: XXX
Address |  | HR/SZ: Hellier St; HR/KA: Hellier St; KA/HR: Armstrong Dr; HR/SZ: Armstrong Dr
PM + CSC |  | HR/SZ: HR/SR; HR/KA: HR/SR; KA/HR: HR/SR; HR/SZ: HR/SR
Funding Type |  | HR/SZ: Solution 2; HR/KA: Solution 2; KA/HR: Solution 2; HR/SZ: Solution 2
Volunteer #s |  | HR/SZ: 8; HR/KA: 8; HR/SZ: 0
Project Cost |  | HR/SZ: 21000; HR/KA: 26000; KA/HR: $; HR/SZ: 57000
Client Name |  | HR/KA: XXX
Address |  | HR/KA: Chippewa St
PM + CSC |  | HR/KA: PN/KA
Funding Type |  | HR/KA: Viatris/Ida
Volunteer #s |  | HR/KA: 12
Project Cost |  | HR/KA: 40000
Client Name
Address
PM + CSC
Funding Type
Volunteer #s
Project Cost

## Active
Active Projects
CLIENT INFORMATION | [5 empty] | Historic Data | CONSTRUCTION NOTES |  |  | DATES |  |  | COST |  |  |  | OTHER
Client Name | Address | City | Phone | CSC | PM | NOTES / Action Items | START DATE | END DATE | LockBox Code | INITIAL WALK | GC WALK | NTP SENT | PROJECT COST | FUNDING SOURCE | FEMA FUNDS | INSURANCE FUNDS | Volunteer | BIO | Fortified | WHP | Presentations | Warranty
Active Projects
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Client Services
Client Services
CLIENT INFORMATION | [5 empty] | NOTES / Action Items | CONSTRUCTION NOTES |  |  | DATES |  |  | COST |  |  |  | OTHER
Client Name | Address | City | Phone | CSC | PM | NOTES / Action Items | START DATE | END DATE | LockBox Code | INITIAL WALK | GC WALK | NTP SENT | PROJECT COST | FUNDING SOURCE | FEMA FUNDS | INSURANCE FUNDS | Volunteer | BIO | Fortified | WHP | Presentations
Client Presentations
Approved, ON DECK TO PRESENT
Pending CEM Approval
Applications in Progress
Denial

## Completed
2023 Completed Projects
CLIENT INFORMATION | [5 empty] | NOTES / Action Items | CONSTRUCTION NOTES |  |  | DATES |  |  | COST |  |  |  | OTHER
Client Name | Address | City | Phone | csc | PM | NOTES / Action Items | START DATE | END DATE | LockBox Code | INITIAL WALK | GC WALK | NTP SENT | PROJECT COST | FUNDING SOURCE | FEMA FUNDS | INSURANCE FUNDS | Volunteer | BIO | Fortified | WHP | Presentations | Warranty
Completed Projects

## RAF (hidden)
RAF TRACKING
CLIENT INFORMATION | [7 empty] | DATES | [12 empty] | COST | [5 empty] | Restore Case Manager | REFERRAL SOURCE | NOTES
Client Name | Address | City | Phone | DESCRIPTION | HOME RISK | SCOPE OF WORK LINK | LOCKBOX CODE | ADDED TO TRACKER | PRE-WALK | ALL DOCS RECEIVED | INITIAL WALK | RESTORE SURVEY | Construction Start | Construction End | RESTORE APPLICATION SUBMITTED | Damage Assessment Completed | Award Acknowledgement | Appeal Submitted | Award Accepted | Check Received | HOME VALUE | FLOODPLAIN | ESTIMATED PROJECT COST | PROJECT COST | FEMA FUNDS | INSURANCE FUNDS
Reimbursement
Allyson Dickerson | 5403 Hwy 18 | Vacherie | 678-613-9244 | majority of the damaged areas have been repaired by the homewner. the HVAC system still needs to be repaired, the roof has been repaired, the scope is just to finish up a bathroom and some minor electrical items in a master bedroom | very feasible | SOW | 4542 |  | 2022-07-11 |  | 2022-07-19 | completed | 2023-10-10 | 2023-11-21 | [6 empty] | 33750 (2022) | 500 yr | $15,000-this does not include HVAC sub cost. | Estimate (SBP) | 16000 | 0 |  | Hope Disaster | 7/20: needs fema + proof of ownership 8/9: sending in docs, verifying fema before sending subs 8/16: scheduling walk for friday, left vm about restore survey pw 8/29: need Legacy walk, 2022 retirement letter 8/29: submitted complaint about fema
Mary Ann Hadley | 310 Greenville St | Raceland | 504-559-9320 | Home has severe mold. There has been a metal roof put on, some gutting completed by the homeowner on the interior, and some work/sheetrock installed on the interior. Overall the scope is relatively straightforward and there are no red flags. Gutting, drywall replacement, mold remediation, insulation, flooring/some subfloor repairs, interior painting, exterior siding and fascia repair 2/17 all Restore documents sent to them 2/20: Restore reimbursement received | feasible | SOW | 1020 |  | 2022-08-10 |  | 2022-08-17 | 2022-08-12 | 2023-10-24 | 2023-11-30 | 2022-12-08 | 2023-12-28 | 2023-02-22 |  | 2023-03-06 |  | 13300 | 100 | 40000 | Estimate (NTP) | 9629 | 0 | Luke Thomas / luke.thomas@restore-la.org | Community Event | 8/8: construction walk scheduled for 8/11 8/11: construction walk for 9am wednesday 8/25: working through flood insurance issue 11/7: SR called, Quitin dissatisfied with construction quality and communication from subs
Zelda Washington | 2724 Yorktown Dr | Laplace | (504) 615-9240 | this home is gutted. the roof still has a tarp on it. the electrical will need to be inspected, as well as the HVAC system. this home did take on over 4' of water | home is almost fully gutted, did take on water, is a feasible job the only challenge is the cost of the job vs the value of the home. | SOW | 0001 |  | 2022-07-19 |  | 2022-07-19 | 2022-07-19 | 2023-10-17 | 2023-12-12 | 2023-12-23 | [5 empty] | 88000 | 100 | 98000 | Estimate (SBP) | 8816 | 17000 |  | Hope Disaster | 7/15: walk scheduled for 7/19 + doc/app pickup. emailed survey link 7/20: needs proof of ownership + fema + insurance 8/8: replacing roof on her own with insurance funds 8/9: need scope + estimate for work completed, substantial damage tool. subs after 8/29: need insurance clarified, estimator walked 8/27 1/11: ZW got an email 1/10 that app was submitted, GZ confirmed 1/11. Confirmed with ZW about next steps and to call when she hears from LBP inspector/damage assessor
Gwen Jackson-Green | 3410 Wall Blvd | New Orleans | 504-762-0175 | Mailed intake docs 9.8 9/19: SD+GZ walk for 9/20 TJ & HR walked. Sub walks week of 10/17 Start file 11/22 damage assessment scheduled for 2/28 2/17: all Restore documents are sent in |  | SOW | 3205 |  | 2022-09-20 |  | 2022-09-29 | 2022-10-28 | 2023-11-30 | 2023-01-13 | 2023-01-17 | 2023-02-28 |  |  |  |  | 83600 | X | $30-40k | Estimate (SBP) | 20868.51 | 0 | Phyllis Potlongo | family/friend | 9/8: dropping off app + docs next week 9/20: Intake/Pre-walk 9/29: Initial Walk 2/2: reached out to Restore contact to schedule walk, left message 2/28: Damage Assessment with Restore
Raymond Wright | 3033 Berwick St | Jefferson | 504-606-0225 |  |  | SOW | 3991 | 2022-11-21 | 2022-11-21 |  | 2022-12-06 | 2022-12-07 | 2023-01-26 | 2023-03-03 | 2023-03-07 | [5 empty] | 2820 | X |  | Estimate (SBP) | 10000 | 0 |  | OOR | 11/21: SZ referral 12/2: application submitted, pre-walk scheduled for 12/2, & con walk scheduled for 12/6 12/7: restore survey completed 1/9: RW to call FEMA hotline for clarification on insurance 1/13: SR called, scheduled Steve meeting on 1/17 and asked questions for client bio 1/20: SR called to schedule start file for 1/24 and construction prep to start 1/26 1/30: SR called to confirm Raymond is aware of outstanding property taxes and has been in touch with parish about it. Raymond called to ask if light switch in garage can be added to SOW. 2/1: Raymond invited to apply to restore 2/24: range hood should have been installed 2/27, close out next week 3/1: range hood to be installed today
Melinda Livas | 300 Hanson Dr | Houma | 985-209-4302 | 3/9: scheduling time to complete restore app over phone, sending close out via docusign |  | SOW | 7274 | 2022-10-27 | 2022-11-01 |  | 2022-10-28 | 2022-11-02 | 2023-01-05 | 2023-02-15 | [6 empty] | 84100 | 500 |  | Estimate (SBP) | 22161.51 | 0 |  |  | pre-walk 10/27 10/31: SR called. Scheduled intake call for 11/1, construction walk 11/2 11/1: intake complete 11/4: SR called to check on app progress, ML had difficulty accessing pdf so form was resent 11/9: HR dropped off app. SR scheduling sub walk for wed 11/14: SR called, left vm 1/9: SR called to touch base on construction and will send color agreement form when ready 1/16: interior work to be finished tomorrow, exterior work to start when siding is delivered 1/24: SR called re ICF survey and doorknob 2/24: HR checking in with TJ about weather strips 3/1: SD to install weather strips 3/2
Active Projects
Elsie Lewis | 1006 Reverend Richard Wilson Dr | Kenner | 504-400-1646 | SD Pre-walk: Half of home is fully gutted including subfloor. There exterior damage to the brickwork and a section of the brick appears to be uniformly separating from the rest of the house. The roof has been repaired but flashing and capping is required. 2/17: Align with Doug on call with Elsie for welcome home party | This would be a larger project outside of the floodplain. Concern regarding the separation of the brick | SOW | 1019 | 2023-08-04 | 2022-08-04 |  | 2022-08-11 | 2022-08-16 | 2023-10-17 |  | received | [5 empty] | 2230 | X | 60000 | Estimate (SBP) | 18000 | 0 |  | Flyer/Poster | 8/3: in person intake scheduled for 8/4 8/5: schedule construction walk + check with Keith for costs 8/8: construction walk scheduled for 8/11 8/16: working to submit docs this afternoon 8/25: need fema letter 2/28: constructioning finishing up EOW, final walkthrough + punch items to follow. Confiming about timeline for moving in, when applicances can be installed
Marlene Harper | 3848 Eastview Dr | Harvey | 504-510-6457 | 9/16: intake/walk scheduled for 9/20 TJ & HR walked. Sub walks week of 10/17 10/19: sent GP ROI Check for appliances 11/7: SR called to update on FEMA appeals Start file 11/22 |  | SOW | 6509 | 2023-09-20 | 2022-09-20 |  | 2022-09-27 | previously completed | 2022-12-05 |  | received | [5 empty] | 6700 | X | $60-80k | Estimate (SBP) | 9779.5 | 0 |  |  | 9/20: intake/Pre-walk 9/27: Initial Walk. Need application, income, FEMA letter, ownership 2/28: construction to finish up EOW, final walkthrough + punch items to follow. Confirming about fridge
Lisa + Oday Mashia | 239 St. Charles St | Destrahan | 916-308-5725 | 3/9: need construction update |  | SOW | 6318 | 2022-10-28 | 2022-11-10 |  | 2022-12-01 | 2022-11-15 | 2/16/2023 + 3/8 |  | received 1/31 | [5 empty] | 77360 | 500 |  | Estimate (SBP) | 12000 | 0 |  |  | 11/15: prewalk & Restore survey completed 11/17: scheduling HR+TJ initial walk for 12/1 11/23: Construction walk scheduled for 12/1 and proof of income docs to be collected on that day 1/13: SR called, left vm, and sent text to schedule steve check-in on tues. 1/18: SR called, Oday and Lisa do not have another location to stay at during construction 1/20: SR called to schedule Hannah & legacy walk for Tues. 1/24 2/24: construction waiting on permits
Scope & Estimate
Veronica Clement Watson | 537 Meyers Blvd | Marrero | 504-342-5266 | 3/9: need construction update |  |  |  | 2023-01-13 | 2023-01-27 |  | 2023-02-08 | previously completed |  |  | received | [5 empty] | 21900 | close to 100 |  |  | 18000 |  |  | Contractor
Gayle Duplantis Landry | 301 Central Ave | Houma | Terrebonne | 3/9: discuss feasibility with HR + TJ | [6 empty] | 2023-03-06 | 2023-06-20 |  |  | received | [5 empty] | 123500 | 500 |  |  | 9629.52 |  | Sherry Liner | TCOA
Blanche Doucet | 818 Chene Dr | Houma | 985-860-3205 | 3/9: discuss feasibility with HR + TJ |  |  |  | 2023-01-30 | 2023-02-14 | 2023-02-28 | 2023-03-06 | previously submitted |  |  | received 2/2 | [5 empty] | 176850 | 100 |  |  | 30239 |  | Sherry Liner | TCOA | 1/30: referral from Sherry Liner 2/2: Sent sherry app and intake docs 2/7: SR called sherry, she's still gathering all the req. docs 2/13: SR left vm to schedule pre walk 2/14: waiting on income docs + Restore update 2/17: received income docs, IDs, utility bills, and verified that she has not submitted application 2/27:HR walk for 3/6
Charlotte + Eloria Phipps | 1806 Frenchmen | New Orleans | 504-669-3367 | 3/9 Docs needed: Marriage cert, title report HR walk scheduled 3/13 |  |  |  | 2023-02-24 | 2023-11-10 |  | 2023-03-13 | did not submit |  |  |  | 2023-02-24 |  |  |  |  | 91000 | X |  |  | 14073 | 0 |  |  | 2/28: doc pickup tmrw 3/1: need to confirm what work has been done, submit Restore survey after confirming address/name. Need recent fema letters
Initial Walk
James Mercadal | 1902 Industry St | New Orleans | 5042332328 | 3/9: scheduling prewalk, unable to get in touch w james. Need income, homeownership, receipts |  |  |  | 2023-02-24 | [7 empty] | 2023-02-24 |  |  |  |  | 61000 | 500 (100 in previous map) |  |  | 9629 | 0 |  |  | 2/24: FEMA initial awards received from DAP. Reaching out for intake 3/8: SD road home covenant but home no longer in the 100 year floodplain. Has owned home longer than online public records.
Denise Crump Smith | 7832 Star St | New Orleans | 504-382-1511 | Get FEMA appeal estimate from Joseph - $20k 3/9: need receipts, 1040, restore survey |  |  |  | 2023-03-02 | 2023-03-09 |  | 2023-03-13 |  |  |  |  | 2023-03-02 |  |  |  |  | 2810 | 500 |  |  | 8129.52 | 0 |  |  | 3/8: Road home covenant but no longer in floodplain. Deed found.
Joseph Batieste | 141 Bishop Dr. | Avondale | 510-707-1715 | 3/8: sent to Giselle for rental assistance appeal 3/9: need flood insurance |  |  |  | 2023-03-03 | 2023-03-07 |  |  | 3/7 |  |  |  | 2023-03-03 |  |  |  |  | 7500 | 100 |  |  | 9000 | 0 |  |  | 3/2: Referral from Sam 3/3: Added to salesforce, Intake call
Application in Progress
Michael and Ada Parker | 2621 Larry St | Houma | 985 647-1408 | Docs needed: Receipts, FEMA info. ROI sent to Giselle 3/3 |  |  |  | 2023-02-22 | 2023-03-02 |  |  | did not submit |  |  |  | 2023-02-22 |  |  |  |  | 20000 | 100 (PFIRM) 500 on effective map |  |  | 20000 | 0 | none |  | 2/22: SR completed pre-app, mostly flooring repairs needed 2/28: prewalk scheduled for 3/2
Annette + Marquis Cooper | 602 S Cumberland | River Ridge | 225-568-7259 |  |  |  |  | 2023-03-01 | [7 empty] | 2023-03-01 |  |  |  |  | 22000 | 100
FEMA Appeal Clients
Kenneth Breaux | 4402 Country Drive | Bourg | (985) 804-9639 | [18 empty] | 100 | [6 empty] | 11/21: still needs to confirm initial FEMA amount 12/22: total award appears $16,559. Confirm address with Sherry Liner 3/8: SD- No road home covenant found. Deed found
Robert Jackson | 2532 N. Courseault St | Lutcher | 9858172660 | [18 empty] | 500 | [6 empty] | 11/21: Initially received $3234, awarded $6701 after appeal for a total of $9935 12/9: Left VM 12/22: SR called. Robert's daughter will call back to complete intake
Lafern Jones | 2602 Truman St | Houma | (985) 856-8445 | [18 empty] | 100 in PFIRM, 500 in effective | [6 empty] | 11/21: Initially received $4444, awarded $5185 for HR and $672 for PP totalling $10301 12/9: Left VM 12/22: SR called. Left VM 3/8: SD- no road home covenant found. JoP for Lafern Jones.
Debra Jones | 118 Exeter Run | Houma | (985) 991-2974 | [18 empty] | 500 | [6 empty] | 3/8: SD - Need to get ROI back from client 3/8: SD - no road home covenant found. Deed found.
Shirley Poole | 309 Senate Dr | Avondale | (504) 270-5797 | [18 empty] | Very close to 100 |  |  | 6800 |  |  |  | 3: SD - no road home covenant. JoP found
Deborah Johnson | 3127 Thomas St. | New Orleans | (504) 326-9842 | [18 empty] | X |  |  | 6000 |  |  |  | 3/8: SD - no road home covenant found. Deed found
Irving Hadley | 3404 Angelique Dr | Violet | (504) 615-2283 | [18 empty] | 500 |  |  | 7000
Eddie Simmons | 1727 N Broad | New Orleans | (504) 701-4001 | [18 empty] | 500 |  |  | 5944 |  |  |  | 3/8: SD - road home covenant but not in floodplain.
Elaine Mitchell | 5841 Lacomb Ave | Marrero | 504-232-0395 | [18 empty] | X |  |  | 5944 |  |  |  | 3/8: SD - road home covenant but not in floodplain.
Chaunte Humble | 4762 St Ferdinand Dr | New Orleans | (504) 563-8396 | [18 empty] | 500 |  |  | 5944 |  |  |  | 3/8: SD - no road home covenant. Succession affadavit recorded
Application on Hold
Manuela Bosley Carr | 1151 Lawrence st | Lutcher | 225-508-0042 | SD Pre-walk: house is nearly all gutted. Will require HVAC, roof, drywall in all rooms | Client is on hold until Restore ownership qualifications can be met. |  |  |  | 2022-07-18 |  | 2022-08-01 | 2022-07-20 | [8 empty] | 10920 | 500 yr flood plain |  |  | 8129 | 0 |  | LAJRN/FEMA Appeals | 7/14: completed pre-app 7/18: intake today 7/20: survey+apps complete, collecting docs 8/1: intial walk 8/8: discuss construction costs + get income docs from daughter 8/25: working to get homeowner a succession, talking to CB
Lorencia Raffray | 520A Locust St | Thibeaudeux | 985-713-2150 | Roof, floor, and wall damage |  |  |  | 2023-01-04 | 2023-01-04 | [6 empty] | 2023-01-04 |  |  |  |  | 1200 | 500 |  |  | 8000 |  |  | Radio ad | 1/4: SR completed initial eligibility assessment and sent application (*Lorencia said she and her brother were the homeowners, but Lafourche assessor's website does not confirm) 1/9: SR left vm checking in on application and offered to schedule pre-walk 1/13: SR called, Lorencia's home is not a manufactured unit, she may need a succession (but is willing to do that), and will let us know when she can schedule a pre-walk next week 1/20: SR called, left vm to check in on paperwork progress 1/24: Lorencia texted that she will call us when the paperwork is completed 2/22: Lorencia sent in paperwork, but may have applied to restore- needs communication designee form to verify
Deborah Mart | 147 Marietta Pl | Houma | 985-855-3331 | Rebuilding Together is replacing roof + gutting house. Confirmed with Sherry that SBP can follow |  |  |  | 2023-02-07 | [7 empty] | 2023-02-07 | [5 empty] | X |  |  |  | 24k |  | Sherry Liner | 2/23: Reached out to Sherry about insurance cap + docs, waiting on response
Elton Billiot | 4013 Oak Pointe Road | Montegut | 985-398-2078 |  |  |  |  | 2022-12-12 | [7 empty] | 2022-12-12 | [5 empty] | 100 |  |  | 20000 |  |  |  | 12/12: SR called, Completed initial eligibility assessment. 1/4: Scheduled pre-walk for 1/10 1/9: SR called to confirm and remind about docs needed. 1/10: could not complete pre-walk. will reschedule for next week. 2/2: Called to inform him that app and intake docs will be delivered through mail

## Gantt
Project | PM | CS | NTP Date | Scheduled Last Day | Actual Last Day |  | Jan | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Febuary | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | March | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | April | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | May | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | June | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | July | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | August | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | September | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | October | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | November | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | December | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
PROJECTS BELOW HERE ARE ACTIVE
IDA CONSTRUCTION
XXX | PN | ET | 2023-07-26 | 2023-08-16 |  | Schedule | [220 empty] | D/F | D/F | D/F | D/F |  |  | P/T | P/T | P/T | P/T | P/T |  |  |  |  | Close Out
Actual
Notes
Problem Category
XXX | PN | KA | 2023-06-19 | 2023-08-11 |  | Schedule | [220 empty] | G/S | G/S | G/S | D/P/FP | [6 empty] | Close Out
Actual
Notes
Problem Category
XXX | PN | KA | 2023-08-07 | 2023-09-27 |  | Schedule | [226 empty] | D/I | D/I | D/I | P | P |  |  | M/Tx | M/Tx | M/Tx | M/Tx | M/Tx |  |  | P | P | P | P | P |  |  | FL | FL | FL | FL |  | FL |  |  | D/Tr | D/Tr | D/Tr | D/Tr | D/Tr | [18 empty] | Close Out
Actual
Notes
Problem Category
Schedule
Actual
Notes
Problem Category
OOR CONSTRUCTION (OCD/OAHMP/VHRMP/TORNADO)
XXX | PN | KA | 2023-06-22 | 2023-09-08 |  | Schedule | [197 empty] | DM | DM | DM | DM | DM |  |  |  | DM | DM | DM |  |  |  | SUB | SUB | SUB | SUB | SUB |  |  | SUB |  | FL | FL | FL | FL |  |  | Tr | Tr | Tr | Tr | Tr |  |  | Close? | [25 empty] | Close Out
Actual
Notes
Problem Category
Schedule
Actual
Notes
Problem Category
Schedule
Actual
Notes
Problem Category
RAF/SOLUTION 2 CONSTRUCTION
XXX | HR | SR | 2023-04-20 | 2023-07-12 |  | Schedule | [114 empty] | RF | RF |  | RF | RF | RF | RF/SFG | SFG | SFG |  |  | CM/DM | CM/DM | CM/DM | CM/DM | CM/DM |  |  | MR/I | MR/I | MR/I | DW | DW | DW |  | DW/IPT | IPT | IPT | IPT | IPT |  |  | IPT/T | IPT/T | T/MEP | T/MEP | T/MEP |  |  | T/MEP | MEP | FP |  | FP | FP |  |  | FP | FP | FP | FP | FP |  |  | FP/FC
[6 empty] | Actual | [114 empty] | RF | RF |  | RF | RF | RF | RF/SFG | SFG | SFG | [9 empty] | - | - | - | - | - | - | [15 empty] | - | - | - |  | HOLD | HOLD |  |  | HOLD | HOLD | HOLD | HOLD | HOLD
[6 empty] | Notes | [125 empty] | Hold interor as clients needed additional week to move out | [6 empty] | permit applied for but determined that appraisal is needed. hold on interior likely 2 week delay | [23 empty] | just received appraisal, submitted to permit office |  |  |  |  | WALKTHROUGH W/ CLIENT?
Problem Category
XXX | HR | SR | 2023-05-26 | 2023-08-11 |  | Schedule | [157 empty] | D/RF | D/RF |  |  | D/FR/RF | D/FR/RF | D/FR/RF | PL/RF | PL/RF | PL |  | PL/O | PL/O | O | O/T | T |  |  | T | T | T | T | T |  |  | T/P/DR | P/DR | P/DR | P/DR | P/DR |  |  |  | P/DR |  | P/DR | P/DR | P/DR |  |  | P/DR | P/DR | P/DR | P/DR | P/DR |  |  | P/DR | P/DR | P/DR | P/DR | P/DR |  |  | P/DR | P/DR | C | C | C |  |  | FC
Actual
Notes
Problem Category
XXX | HR | SZ | 2023-06-23 | 2023-09-08 |  | Schedule
Actual
Notes
Problem Category
XXX | HR | SZ | 2023-06-30 | 2023-09-08 |  | Schedule
Actual
Notes
Problem Category
XXX | HR | SZ | 2023-07-01 | 2023-09-30 |  | Schedule
Actual
Notes
Problem Category
XXX | HR | SZ | 2023-07-27 | 2023-09-30 |  | Schedule
Actual
Notes
Problem Category

## 2022 Construction WB (hidden)
KEY | Month | Goal | Actual | Predicted Projects (starts/completes) this month |  |  |  |  | Month | Goal | Actual | Predicted Projects (starts/completes) this month | [6 empty] | Month | Goal | Actual | Predicted Projects (starts/completes) this month | [6 empty] | Month | Goal | Actual | Predicted Projects (starts/completes) this month | [6 empty] | Month | Goal | Actual | Predicted Projects (starts/completes) this month
Spend: weekly construction funds spent across all grant programs | August |  |  | PM | NTP's/Starts |  |  |  | September |  |  | PM | NTP's/Starts |  |  | PM | NTP's/Starts |  | October |  |  | PM | NTP's/Starts |  |  | PM | NTP's/Starts |  | November |  |  | PM | NTP's/Starts |  |  | PM | NTP's/Starts |  | December |  |  | PM | NTP's/Starts |  |  | PM | NTP's/Starts
NTP's: # of NTP's sent during that respective week | Spend | 226734.67 | 20 | HR | Sheila Brown: 199 Willard St | Timeline Initial Walk:8/8 Scope Completed:8/10 Sub Walk:8/10 Estimate Completed: Start File: |  |  | Spend |  |  | HR | Sheila Brown: 199 Willard St | Timeline Initial Walk:8/8 Scope Completed:8/10 Sub Walk:8/10 Estimate Completed: Start File: |  | HR | Vernetta Matthews: 6115 N. Johnson St | Timeline Initial Walk:9/8 Scope Completed:9/12 Sub Walk:9/13 Estimate Completed:9/21 Start File:9/26 | Spend |  |  | HR | Sheila Brown: 199 Willard St | Timeline Initial Walk:8/8 Scope Completed:8/10 Sub Walk:8/10 Estimate Completed: Start File: |  | PN | Diane Washington: 1427 Jourdan Ave | Timeline Initial Walk: 9/22 Scope Completed: 10/5 Sub Walk: 10/17 Estimate Completed: 10/26 Start File: 10/28 | Spend |  |  | HR | Sheila Brown: 199 Willard St | Timeline Initial Walk:8/8 Scope Completed:8/10 Sub Walk:8/10 Estimate Completed: Start File: NTP: |  | HR | Sandra Nunnery: 26 Furman Circle | Timeline Initial Walk:11/8 Scope Completed:11/14 Sub Walk:11/21 Estimate Completed:11/24 Start File:11/29 NTP:11/30 | Spend |  |  | HR | Sheila Brown: 199 Willard St | Timeline Initial Walk:8/8 Scope Completed:8/10 Sub Walk:8/10 Estimate Completed: Start File: NTP: |  | HR | Valander Steele: 2005 St Roch Ave | Timeline Initial Walk:11/14 Scope Completed:12/6 Sub Walk:11/29 Estimate Completed:12/6 Start File:12/12 NTP:12/13
Completes: # of jobs completed during that respsective week | NTP's | 14 | 2 | PN | Betty Dison: 4000 Najolia St | Timeline Initial Walk: 7/27 Scope Completed:8/15 Sub Walk: 8/16 Estimate Completed: Start File: |  |  | NTP's | 15 | 10 | PN | Betty Dison: 4000 Najolia St | Timeline Initial Walk: 7/27 Scope Completed:8/15 Sub Walk: 8/16 Estimate Completed: Start File: |  | HR | Joyce Williams: 435 Authement St | Timeline Initial Walk: 9/7 Scope Completed:9/12 Sub Walk: 9/14 Estimate Completed:9/22 Start File:9/30 | NTP's | 17 | 14 | RG | Larry Valentine: 8611 Jeannette St | Timeline Initial Walk:9/16(HR walked for Ida, indicated OAHMP), walked 10/25 with OT Scope Completed: (OT recommendations 11/3)11/4 Sub Walk:11/15 Estimate Completed:11/16 Start File: |  | PN | Joe Smith: 1901 Saint Maurice Avenue | Timeline Initial Walk: 9/22 Scope Completed: 10/5 Sub Walk: 10/17 Estimate Completed:10/26 Start File: 10/28 | NTP's | 13 | 15 | RG | Larry Valentine: 8611 Jeannette St | Timeline Initial Walk:9/16(HR walked for Ida, indicated OAHMP) 10/25 with OT Scope Completed:(OT recommendations 11/3) 11/4 Sub Walk: 11/15 Estimate Completed:11/16 Start File: NTP: 11/30 |  | HR | Paul Tricuit: 3963 Pauger St | Timeline Initial Walk:11/15 Scope Completed:11/15 Sub Walk: 11/15 Estimate Completed:11/21 Start File:11/23 NTP:11/23 | NTP's | 5 | 3 | HR | Betty Cannon: 313 Hellier St | Timeline Initial Walk:11/2 Scope Completed:11/11 Sub Walk:11/16 Estimate Completed: Start File: NTP: |  |  |  | Timeline Initial Walk: Scope Completed: Sub Walk: Estimate Completed: Start File: NTP:
Change Orders: # of change orders AND total amount spent | Completes | 11 | 2 | PN | Myrtle Plummer: 2156 Carnot St | Timeline Initial Walk: 8/2 Scope Completed: 8/10 Sub Walk: 8/11 Estimate Completed:8/30 Start File:8/30 |  | 2022-08-31 | Completes | 11 | 10 | RG | Mary Pierce: 655 Lee's Lane | Timeline Initial Walk: Scope Completed: Sub Walk: Estimate Completed: Start File: |  | PN | Jeanette Williams | Timeline Initial Walk: Scope Completed: Sub Walk: Estimate Completed: Start File: | Completes | 12 | 6 | RG | Mary Pierce: 655 Lee's Lane | Timeline Initial Walk:10/6 Scope Completed:10/13 Sub Walk:n/a Estimate Completed:10/13 Start File:10/18 |  | PN | Jeanette Williams: 2407 Desire St | Timeline Initial Walk: 9/2 Scope Completed: 9/20 Sub Walk: 9/28 Estimate Completed: 10/26 Start File: 10/27 | Completes | 15 | 12 | HR | Michael Craft: 1310 Touro St. | Timeline Initial Walk:10/10 Scope Completed:10/18 Sub Walk:10/19 Estimate Completed:11/1 Start File:11/3 NTP: 11/3 |  | HR | Joi Aikins: 1521 Seville Dr | Timeline Initial Walk:11/21 Scope Completed:11/24 Sub Walk: N/A Estimate Completed:11/24 Start File:11/28 NTP:11/30 | Completes | 17 | 11 | HR | Melinda Livas: 300 Hanson Dr | Timeline Initial Walk:11/2 Scope Completed:11/11 Sub Walk:11/16 Estimate Completed:12/16 Start File:1/4 NTP: |  |  |  | Timeline Initial Walk: Scope Completed: Sub Walk: Estimate Completed: Start File: NTP:
| Change Orders | 0 | 1 | HR | Mark Jackson: 1839 E. Homestead St | Timeline Initial Walk:8/9 Scope Completed: 8/12 Sub Walk: 8/16 Estimate Completed:8/24 Start File:8/25 |  | 2022-08-25 | Change Orders | 0 |  | HR | Thomas & Destiny: 124 Leger St. | Timeline Initial Walk:8/26 Scope Completed:9/13 Sub Walk: 9/14 Estimate Completed:9/22 Start File:9/28 |  |  |  |  | Change Orders | 0 |  | PN | Betty Dison: 4000 Najolia St | Timeline Initial Walk: 7/27 Scope Completed:8/15 Sub Walk: 8/16 Estimate Completed: 10/12 Start File: 10/13 |  | HR | Rosie Youngblood: 813 Wagner St | Timeline Initial Walk:9/26 Scope Completed:9/26 Sub Walk:9/27 Estimate Completed:10/12 Start File:10/12 | Change Orders | 0 |  | PN | Dan Leyrer: 1028 Joliet St. | Timeline Initial Walk: 10/10 Scope Completed:11/15 Sub Walk: 11/16 Estimate Completed: 11/29 Start File: 11/30 NTP: 11/30 |  |  |  |  | Change Orders | 0 |  | RG | Delores Williams: 8630 Marks St | Timeline Initial Walk:12/6 Scope Completed: Recs received 12/21, scope complete 12/21 Sub Walk:12/22 Estimate Completed: Start File: NTP:
|  |  |  | HR | Kimberly Matthews: 4334 Randolph Ave | Timeline Initial Walk:8/9 Scope Completed:8/12 Sub Walk: 8/16 Estimate Completed:8/23 Start File:8/24 |  | 2022-08-24 |  |  |  | PN | Linda Triggs: 5937 South Oak Drive | Timeline Initial Walk: 8/22 Scope Completed:8/24 Sub Walk: 8/25 Estimate Completed: 9/29 Start File: 9/29 | [7 empty] | PN | Errol Duvernay: 4359 Van Avenue | Timeline Initial Walk: 9/8 Scope Completed:9/26 Sub Walk: 9/27 Estimate Completed: Start File: |  | HR | Lisha Batiste: 2732 Hardwood Dr. | Timeline Initial Walk:10/10 Scope Completed:10/18 Sub Walk:10/19 Estimate Completed:10/27 Start File:10/28 |  |  |  | PN | Anthony Myles: 918 Pine St. | Timeline Initial Walk: 10/13 Scope Completed: 11/4 Sub Walk: 11/4 Estimate Completed: 11/20 Start File: 11/21 NTP: 11/22 | [7 empty] | PN | Ciara Ricks: 168 Yvonne St | Timeline Initial Walk: 11/4 Scope Completed: 11/15 Sub Walk: 11/16 Estimate Completed: 12/13 Start File: 12/13 NTP: 12/15
| Week 1 |  |  | PN | Keion Smith: 3636 Timberwolf Lane | Timeline Initial Walk: 8/8 Scope Completed: 8/10 Sub Walk: 8/11 Estimate Completed: 8/30 Start File: 8/31 |  | 2022-08-31 | Week 1 |  |  | PN | Kristy Carter: 1124 Flood St. | Timeline Initial Walk: 8/29 Scope Completed: Sub Walk: Estimate Completed: 9/28 Start File: 9/28 |  |  |  |  | Week 1 |  |  | PN | Joelle Fisher: 207 Warrington Drive | Timeline Initial Walk: 9/6 Scope Completed: 10/5 Sub Walk: 10/6 Estimate Completed: Start File: |  |  |  |  | Week 1 |  |  | HR | Detherita Parker: 3411 Marigny St. | Timeline Initial Walk:10/17 Scope Completed:10/24 Sub Walk:10/25 Estimate Completed:11/4 Start File:11/4 |  |  |  |  | Week 1 |  |  | PN | Dung Le: 3239 Chimney Ln | Timeline Initial Walk: 11/2 Scope Completed: 11/15 Sub Walk: 11/16 Estimate Completed: Start File: NTP:
| Spend |  |  | PN | Pamela Howard: 912 Silver Lily Lane | Timeline Initial Walk: 8/8 Scope Completed: 8/10 Sub Walk: 8/11 Estimate Completed: 8/30 Start File: 8/30 |  | 2022-08-31 | Spend |  |  | PN | Joseph Morgan: 1859 Pleasure St. | Timeline Initial Walk: 8/29 Scope Completed: Sub Walk: Estimate Completed: 9/28 Start File: 9/28 |  |  |  |  | Spend |  |  | HR | Mary Anne Hadley: 310 Greenville St. | Timeline Initial Walk: 8/29 Scope Completed:9/7 Sub Walk: 9/12 Estimate Completed:9/18 Start File:10/20 |  |  |  |  | Spend |  |  | HR | Marlene Harper: 3848 Eastview Dr. | Timeline Initial Walk:9/27 Scope Completed:10/17 Sub Walk:10/18 Estimate Completed:10/28 Start File:11/22 NTP:11/23 |  |  |  |  | Spend |  |  | PN | Don Alexander: 825 Wilker Neal | Timeline Initial Walk: 11/11 Scope Completed: 12/8 Sub Walk: 12/9 Estimate Completed: 12/22 Start File: 12/22 NTP:
| NTP's |  | 2 | PN | Raymond Washington: 2801 Holiday St | Timeline Initial Walk: n/a Scope Completed: n/a Sub Walk: n/a Estimate Completed: 8/17 Start File: 8/19 |  | 2022-08-23 | NTP's |  | 0 | HR | Allyson Dickerson: 5304 Highway 18 | Timeline Initial Walk:7/19 Scope Completed:7/26 Sub Walk:8/19 Estimate Completed:7/26 Start File: |  |  |  |  | NTP's |  | 1 | HR | Allyson Dickerson: 5304 Highway 18 | Timeline Initial Walk:7/19 Scope Completed:7/26 Sub Walk:8/19 Estimate Completed:7/26 Start File: 10/6 |  |  |  |  | NTP's |  | 2 | HR | Gwen Green/Jackson: 3410 Wall Blvd | Timeline Initial Walk:9/29 Scope Completed:10/17 Sub Walk:10/18 Estimate Completed:10/28 Start File:11/22 NTP:11/23 |  |  |  |  | NTP's |  |  | PN | Angela Gatlin: 511 Dakin | Timeline Initial Walk: 11/16 Scope Completed: 12/9 Sub Walk: 12/12 Estimate Completed: Start File: NTP:
| Completes |  | 1 | RG | Thomas Riggio: 7220 Hattie St | Timeline Initial Walk: 6/9 Scope Completed: 7/5 Sub Walk: n/a Estimate Completed: 7/22 Start File: 8/5 |  | 2022-08-08 | Completes |  | 1 | HR | Zelda Washington: 2724 Yorktown Dr | Timeline Initial Walk: 7/19 Scope Completed:7/26 Sub Walk:8/19 Estimate Completed:8/28 Start File: |  |  |  |  | Completes |  | 0 | HR | Zelda Washington: 2724 Yorktowne Dr | Timeline Initial Walk: 7/19 Scope Completed:7/26 Sub Walk:8/19 Estimate Completed:8/28 Start File: 10/5 |  |  |  |  | Completes |  | 3 | HR | Brenda Reese: 920 Third St. | Timeline Initial Walk:11/1 Scope Completed:11/7 Sub Walk:11/8 Estimate Completed:11/11 Start File:11/17 NTP:11/18 |  |  |  |  | Completes |  | 2 | PN | Cynthia Jefferson: 1326 Tennessee St | Timeline Initial Walk: 11/16 Scope Completed: 12/9 Sub Walk: 12/12 Estimate Completed: Start File: NTP:
| Change Orders |  | 2 | RG | Helen Breedlove: 7229 Janssen St | Timeline Initial Walk: 6/30 Scope Completed: 7/21 Sub Walk: 8/5 Estimate Completed: 8/24 Start File: 8/29 |  | 2022-08-30 | Change Orders |  |  | HR | Elsie Lewis: 1006 Reverend Wilson Drive | Timeline Initial Walk:8/11 Scope Completed:8/16 Sub Walk:8/19 Estimate Completed:8/30 Start File: |  |  |  |  | Change Orders |  |  | HR | Elsie Lewis: 1006 Reverend Wilson Drive | Timeline Initial Walk:8/11 Scope Completed:8/16 Sub Walk:8/19 Estimate Completed:8/30 Start File: 10/5 |  |  |  |  | Change Orders |  |  | PN | Errol Duvernay: 4359 Van Avenue | Timeline Initial Walk: 9/8 Scope Completed:9/26 Sub Walk: 9/27 Estimate Completed: 11/17 Start File: 11/18 NTP: 11/18 |  |  |  |  | Change Orders |  |  | PN | Gene Rapp: 3239 Chippewa St | Timeline Initial Walk: 12/5 Scope Completed: Sub Walk: Estimate Completed: Start File: NTP:
|  |  |  | RG | Mary Pierce: 655 Lee's Lane | Timeline Initial Walk: Scope Completed: Sub Walk: Estimate Completed: Start File: | [5 empty] | PN | Sharon Williams: 6110 Lafaye St | Timeline Initial Walk: 8/30 Scope Completed: Sub Walk: Estimate Completed: 9/19 Start File: 9/20 | [7 empty] | PN | Tyrone Muse: 1446 Murl Street | Timeline Initial Walk: 9/21 Scope Completed: 10/14 Sub Walk: Estimate Completed: Start File: | [7 empty] | PN | Tyrone Muse: 1446 Murl Street | Timeline Initial Walk: 9/21 Scope Completed: 10/14 Sub Walk: 10/21 Estimate Completed: 11/21 Start File: 11/22 NTP: 11/22 | [7 empty] | PN | Genique Jones: 2013 N. Roman St | Timeline Initial Walk: 12/2 Scope Completed: Sub Walk: Estimate Completed: Start File: NTP:
| Week 2 |  |  | HR | Cheryl Wilson: 906 E. McAdoo St. | Timeline Initial Walk:8/15 Scope Completed:8/24 Sub Walk:8/25 Estimate Completed:8/29 Start File:8/31 |  | 2022-08-31 | Week 2 |  |  | RG | Alice Wroten: 4566 Cerise St. | Timeline Initial Walk:9/2 Scope Completed:9/9 Sub Walk:9/12 Estimate Completed:9/13 Start File:9/14 |  |  |  |  | Week 2 |  |  | HR | Pamela Jackson: 2137 D'Abadie Street | Timeline Initial Walk:9/16 Scope Completed:9/25 Sub Walk: 9/27 Estimate Completed: Start File: |  |  |  |  | Week 2 | [9 empty] | Week 2
| Spend |  |  | PN | Terrie Horne: 5552 Cameron Blvd | Timeline Initial Walk: 6/6 Scope Completed: Sub Walk: Estimate Completed: Start File: 8/1 |  | 2022-08-01 | Spend |  |  | RG | Florence Gibson: 4374 Randolph Ave. | Timeline Initial Walk:9/2 Scope Completed:9/9 Sub Walk:N/A Estimate Completed:9/9 Start File:9/14 |  |  |  |  | Spend |  |  | HR | Jeanette Bradford: 1604 Cemetery Street | Timeline Initial Walk:9/21 Scope Completed: 9/25 Sub Walk: 9/28 Estimate Completed:10/19 Start File:10/19 |  |  |  |  | Spend |  |  | HR | Wilma Williams: 826 Columbus St | Timeline Initial Walk:10/31 Scope Completed:11/7 Sub Walk:11/9 Estimate Completed:11/11 Start File:11/18 NTP:11/18 |  |  |  |  | Spend |  |  | RG | Creola Blackburn: 2519 N Galvez | Timeline Initial Walk:12/6 Scope Completed:Rec's received 12/21, scope 12/21 Sub Walk: Estimate Completed: Start File: NTP:
| NTP's |  | 0 |  |  | Timeline Initial Walk: Scope Completed: Sub Walk: Estimate Completed: Start File: |  |  | NTP's |  | 2 | HR | Cora Mae Washington: 1013 Hooter Rd | Timeline Initial Walk:9/8 Scope Completed:9/13 Sub Walk:9/14 Estimate Completed:9/21 Start File:9/23 |  |  |  |  | NTP's |  | 5 | HR | Audrey Harrington: 607 Lang Street | Timeline Initial Walk:9/16 Scope Completed:9/25 Sub Walk:9/27 Estimate Completed:10/10 Start File:10/12 |  |  |  |  | NTP's |  |  | PN | Joelle Fisher: 207 Warrington Drive | Timeline Initial Walk: 9/6 Scope Completed: 10/5 Sub Walk: 10/6 Estimate Completed: 11/4 Start File: 11/4 NTP: 11/17 |  |  |  |  | NTP's |  | 2 | RG | Helen James: 1622 Alvar St | Timeline Initial Walk:12/6 Scope Completed:Recs recieved 12/21, scope 12/21 Sub Walk:12/22 Estimate Completed: Start File: NTP:
| Completes |  | 1 |  | Projected Completed Homes |  | Y/N? | DATE | Completes |  | 0 |  | Projected Completed Homes |  | Y/N? | DATE |  |  | Completes |  | 1 |  | Projected Completed Homes |  | Y/N? | DATE |  |  | Completes |  | 1 |  | Projected Completed Homes |  | Y/N? | DATE |  |  | Completes |  | 7 |  | Projected Completed Homes |  | Y/N? | DATE | PM | 2023 Completes | Date
| Change Orders |  |  | HR | Kevin Marie Mimms: 2023 Baronne St |  | TRUE | 2022-08-05 | Change Orders |  |  | PN | Pamela Howard |  | TRUE | 2022-09-30 |  |  | Change Orders |  |  | PN | Myrtle Plummer: 2156 Carnot |  | TRUE | 2022-10-03 |  |  | Change Orders | [9 empty] | Change Orders |  |  | HR | Thomas Hollinger & Destiny Lopez: 124 Leger St |  | TRUE | 2022-12-21 | HR | Marlene Harper: 3838 Eastview Dr | 2023-03-01
|  |  |  | HR | Veronica Harris: 9056 Main St |  | FALSE |  |  |  |  | HR | Kimberly Matthews |  | TRUE | 2022-09-09 | [5 empty] | HR | Mark Jackson: 1839 East Homestead |  | TRUE | 2022-10-28 | [15 empty] | HR | Joi Aikins: 1521 Seville Dr |  | TRUE | 2022-12-12 | HR | Betty Cannon: 313 Hellier St | 2023-01-01
| Week 3 |  |  | HR | Cheramie Jupiter: 7146 W. Main St |  | TRUE | 2022-08-24 | Week 3 | [9 empty] | Week 3 | [9 empty] | Week 3 |  |  | HR | Pamela Jackson: 2137 D'Abadie St |  | TRUE | 2022-11-21 |  |  | Week 3 |  |  | PN | Betty Dison: 4000 Najolia St |  | TRUE | 2022-12-30 | HR | Melinda Livas: 300 Hanson Dr | 2023-01-01
| Spend |  |  | PN | Deanne Thomas: 6061 Paris Ave |  | TRUE |  | Spend |  |  | RG | Helen Breedlove |  | TRUE | 2022-09-30 |  |  | Spend | [9 empty] | Spend |  |  | HR | MaryAnne Hadley: 310 Greenville St. |  | TRUE | 2022-11-29 |  |  | Spend |  |  | PN | Ciara Ricks: 168 Yvonne Dr |  | FALSE |  | PN | Joelle Fisher:207 Warrington Dr | 2023-02-01
| NTP's |  | 2 | PN | Terrie Horne: 5552 Cameron Blvd |  | TRUE | 2022-08-01 | NTP's |  | 2 | RG | Thomas Riggio |  | TRUE | 2022-09-14 |  |  | NTP's |  | 4 | [7 empty] | NTP's |  |  | PN | Sharon Williams: 6110 Lafaye |  | TRUE | 2022-11-03 |  |  | NTP's |  | 1 | PN | Anthony Myles: 918 Pine St |  | TRUE | 2022-12-20 | PN | Dan Leyrer: 1028 Joliet | 2023-01-01
| Completes |  |  | RG | Cindy & Emile: 7211 Easy St |  | TRUE | 2022-08-13 | Completes |  | 3 | HR | Cheryl Wilson |  | TRUE | 2022-09-21 |  |  | Completes |  | 1 | HR | Vernetta Matthews: 6115 N. Johnson St. |  | TRUE | 2022-10-21 |  |  | Completes |  |  | PN | Diane Washington: 1427 Jourdan |  | TRUE | 2022-11-18 |  |  | Completes |  | 2 | HR | Paul Tricuit: 3963 Pauger St |  | TRUE | 2022-12-13 | PN | Tyrone Muse: 1446 Murl | 2023-01-01
| Change Orders |  |  | RG | Genevia Gabriel: 4619 Daneel St |  | TRUE | 2022-08-19 | Change Orders | [9 empty] | Change Orders |  |  | HR | Rosie Youngblood: 813 Wagner Street |  | TRUE | 2022-10-26 |  |  | Change Orders |  |  | PN | Joe Smith: 1901 St. Maurice |  | TRUE | 2022-11-30 |  |  | Change Orders |  |  | PN | Errol Duvernay: 4359 Van Ave |  | TRUE | 2022-12-30 |  | Burnell's: 2043 Flood | 2022-12-21
|  |  |  | TJ | Edgard Crawford: 1433 Tricou |  | TRUE | 8/31/2022 |  |  |  | TJ | Michael Vaughn: 6127 N. Galvez |  | TRUE | 9/27/2022 | [15 empty] | HR | Audrey Harrington: 607 Lang Street |  | TRUE | 2022-11-09 | [5 empty] | PN | Linda Ann Triggs: 5937 S. Oak |  | FALSE
| Week 4 |  |  | TJ | Sandra Melendez: 908 Belleville |  | TRUE | 8/26/2022 | Week 4 |  |  | TJ | Rena Cavanaugh: 608 Lang St. |  | TRUE | 9/29/2022 |  |  | Week 4 | [9 empty] | Week 4 |  |  | PN | Raymond Washington: 2801 Holiday |  | TRUE | 2022-11-16 |  |  | Week 4 |  |  | HR | Gwen Green/Jackson: 3410 Wall Blvd |  | FALSE
| Spend |  |  | TJ | Michael Vaughn: 6127 N. Galvez |  | FALSE |  | Spend |  |  | PN | Keion Smith |  | TRUE | 2022-09-29 |  |  | Spend |  |  | HR | Joyce Williams: 435 Authement St |  | TRUE | 2022-10-21 |  |  | Spend |  |  | PN | Joseph Morgan: 1859 Pleasure |  | TRUE | 2022-11-02 |  |  | Spend |  |  | RG | Larry Valentine: 8611 Jeanette St |  | TRUE | 2022-12-13
| NTP's |  | 5 | TJ | Elizabeth Leslie: 2503 Delery |  | TRUE | 8/26/2022 | NTP's |  | 6? | [7 empty] | NTP's |  | 4 | HR | Cora Mae Washington: 1013 Hooter Rd |  | TRUE | 2022-10-07 |  |  | NTP's |  |  | PN | Kristy Carter: 1124 Flood |  | TRUE | 2022-11-02 |  |  | NTP's |  |  | HR | Michael Craft: 1310 Touro St |  | FALSE
| Completes |  |  | TJ | Rena Cavanaugh: 608 Lang St |  | FALSE |  | Completes |  | 2? | [7 empty] | Completes |  | 3 |  |  |  | FALSE |  |  |  | Completes |  |  | HR | Allyson Dickerson: 5403 Highway 18 |  | TRUE | 2022-11-21 |  |  | Completes |  |  | PN | Jeanette Williams: 2407 Desire |  | TRUE | 2022-11-23
| Change Orders |  | 1 | TJ | Earl Burbank: 3146 Bruxelles St |  | TRUE | 8/31/2022 | Change Orders | [9 empty] | Change Orders | [5 empty] | FALSE |  |  |  | Change Orders |  |  | RG | Mary Pierce: 655 Lee's Lane |  | TRUE | 2022-11-14 |  |  | Change Orders |  |  | HR | Brenda Reese: 920 Third St |  | TRUE | 2022-12-01
[12 empty] | RG | Florence Gibson |  | TRUE | 2022-09-26 | [8 empty] | FALSE | [6 empty] | HR | Detherita Parker: 3411 Marigny St |  | TRUE | 2022-11-18 | [5 empty] | HR | Sandra Nunnery: 26 Furman Circle |  | FALSE
[12 empty] | RG | Alice Wroten |  | TRUE | 2022-09-23 | [8 empty] | FALSE | [16 empty] | HR | Wilma Williams: 226 Columbus St |  | TRUE | 2022-12-09
[5 empty] | AUGUST SUMMARY: STARTS- 10 COMPLETES- 10 SPEND TOTAL- CHANGE ORDER #-8 | [36 empty] | TJ | Burnell's |  | TRUE
[42 empty] | HR | Mona & Andrew Pitre: 1348 Palmisano Dr. |  | TRUE | 2022-12-03
PL Support & Misc Projects: general project lead education/training/development that occurs. Projects that construction team supports that are not directly related to a respsective jobsite. Please reference # of labor hours used on special projects. | PL Support: extended demo on how to install windows extended demo on how to zip tape extended demo on how to install siding pulling together PL training materials for training layout Drywall training/tutorial (1 day w/ all PLs) Installation of exterior door training Discussed siding challenges on site (daily) Daily emails given with guidance to goals/whiteboard Misc Projects: unloaded PVC cabinets. Hrs:15 labor hrs rental OCD maintenance checks. Hrs: 3 labor hrs nursery & dirt hunt for 9/11 vol day. Hrs: 1 labor hr record declaration of title change with CNO. Hrs: 3 labor hrs walked pelicans house for weatherization. Hrs: 3 labor hrs search for generator for SBP HQ. Hrs: 2 labor hrs LA dept of insurance taskforce initiative. Hrs: 2 hrs 22hrs on rental, OAHMP, OH, WH- RG NORA/OH lot permit prep for Phil- TSJ, 1hr State dept insurance prep-2hrs SBP Roof repair- 2hrs | [7 empty] | PL Support: Misc Projects: | [9 empty] | PL Support: Misc Projects: | [9 empty] | PL Support: Misc Projects: | [9 empty] | PL Support: Misc Projects: |  |  | HR | Zelda Washington:2724 Yorktowne Dr |  | TRUE | 2022-12-13
[42 empty] | HR | Lisha Batiste: 2732 Hardwood Dr |  | TRUE | 2022-12-16
[42 empty] | HR | Valander Steele: 2005 St Roch Ave |  | FALSE